## Summary
AX Studio Committed Work Report
Report date | 2026-05-11 |  | Branch | slim/remove-dead-features-clean |  | Range | 2026-05-08 to 2026-05-11
Total commits | 30 |  | Refactor/cleanup commits | 9 |  | Unique files changed | 200
Additions | 9219 |  | Deletions | 2598 |  | Net lines | 6621
Authors | Bhaskar Vora |  | Committed days | 2026-05-08, 2026-05-09 |  | Note | No commits found on May 10 or May 11 in this branch.
Top Work Themes | Commits | Files Touched | Additions | Deletions | Impact
Startup / provider readiness | 13 | 124 | 4056 | 896 | Reduced blank startup states and bounded provider/model readiness waits.
Local knowledge / MCP | 7 | 172 | 4282 | 1317 | More reliable local knowledge retrieval, MCP retry/restart behavior, and hidden context injection.
Model hub / downloads | 3 | 9 | 180 | 63 | Cleaner Hugging Face URL handling, model routing, and MLX discoverability.
Thread and conversation storage | 2 | 8 | 493 | 224 | More resilient message/thread persistence, including native fallback storage.
Local model inference | 2 | 4 | 107 | 13 | Improved local model startup and streaming readiness paths.
Server / proxy hardening | 2 | 6 | 92 | 79 | Centralized CORS/header logic and hardened proxy/model route behavior.
General stability | 1 | 1 | 9 | 6 | Miscellaneous stability fixes and maintenance.

## Daily Timeline
Date | Commits | Additions | Deletions | Net Lines | Primary Focus | Representative Commit Subjects
2026-05-08 | 27 | 7776 | 2410 | 5366 | Thread and conversation storage; Startup / provider readiness; Local model inference; Model hub / downloads | refactor: clean up thread storage handling and flag reads ¦ fix(core): return owned finish_reason string to satisfy lifetimes ¦ chore: add local workspace files pending from sync ¦ Add timeout to extension startup path
2026-05-09 | 3 | 1443 | 188 | 1255 | Startup / provider readiness | Improve local inference readiness and stability ¦ Wait for local model startup before streaming ¦ Avoid local chat startup deadlock

## Commits
Date/Time | Hash | Author | Subject | Category | Additions | Deletions | Files | Key Modules | Notes
2026-05-08 13:01:01 ET | e26fba4 | Bhaskar Vora | refactor: clean up thread storage handling and flag reads | Thread and conversation storage | 94 | 57 | 4 | UI components (1), Thread/chat hooks (1), Web app libraries (1) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 13:01:02 ET | 44bc411 | Bhaskar Vora | fix(core): return owned finish_reason string to satisfy lifetimes | Startup / provider readiness | 28 | 35 | 1 | Server/proxy backend (1) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 13:07:13 ET | c189427 | Bhaskar Vora | chore: add local workspace files pending from sync | Startup / provider readiness | 868 | 0 | 10 | Web app libraries (6), Tests (2), Docs/reports (1) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 13:14:05 ET | f35d74e | Bhaskar Vora | Add timeout to extension startup path | Startup / provider readiness | 9 | 3 | 1 | App providers (1) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 13:14:07 ET | 663f3eb | Bhaskar Vora | Harden provider discovery and registration with bounded timeouts | Startup / provider readiness | 162 | 84 | 2 | Web app libraries (1), Web services (1) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 13:40:08 ET | f40646b | Bhaskar Vora | fix: stabilize startup event bridge and context-size error handling | Startup / provider readiness | 167 | 57 | 7 | Web app libraries (3), App providers (2), Docs/reports (1) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 14:26:37 ET | 6888db8 | Bhaskar Vora | Fix local MLX model discovery in Ax Studio | Local model inference | 96 | 10 | 3 | Tests (1), Llamacpp extension (1), Tauri backend (1) | Improved local model startup, readiness, or streaming behavior.
2026-05-08 14:28:30 ET | e686922 | Bhaskar Vora | Show MLX filter in model hub | Local model inference | 11 | 3 | 1 | Model hub (1) | Improved local model startup, readiness, or streaming behavior.
2026-05-08 14:37:31 ET | ca2b39e | Bhaskar Vora | fix: encode hub model ids and normalize HF links | Startup / provider readiness | 69 | 16 | 3 | Model hub (2), App providers (1) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 14:39:20 ET | cfac31b | Bhaskar Vora | refactor: centralize hub model routing and HF link parsing | Startup / provider readiness | 67 | 45 | 4 | Model hub (2), Web app libraries (1), App providers (1) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 14:41:25 ET | 9c2d47a | Bhaskar Vora | refactor(web-app): consolidate Hugging Face URL helpers | Model hub / downloads | 87 | 22 | 4 | UI components (1), Tests (1), Web app libraries (1) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 14:42:01 ET | aaebeda | Bhaskar Vora | chore(core): apply remaining refactor and cleanup changes | Local knowledge / MCP | 243 | 130 | 18 | Tauri llamacpp plugin (6), Tauri backend (4), Server/proxy backend (4) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 14:44:17 ET | de7fc77 | Bhaskar Vora | refactor(server,huggingface): centralize URL cleanup and endpoint suffix stripping | Model hub / downloads | 60 | 19 | 3 | Server/proxy backend (1), Tests (1), Web app libraries (1) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 14:46:19 ET | 5954ed8 | Bhaskar Vora | refactor(server,tests): centralize upstream-header filtering and reuse hf URL helper in tests | Model hub / downloads | 33 | 22 | 2 | Server/proxy backend (1), Tests (1) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 14:48:23 ET | 6bcf1d2 | Bhaskar Vora | refactor(web): centralize core bridge initialization | Startup / provider readiness | 33 | 38 | 4 | Web app libraries (2), Other (1), App providers (1) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 14:49:32 ET | bad4a8e | Bhaskar Vora | refactor(server): centralize CORS constants | Server / proxy hardening | 91 | 78 | 5 | Server/proxy backend (5) | Refactoring/cleanup: reduced duplication and centralized shared logic.
2026-05-08 14:50:42 ET | 0ba1f97 | Bhaskar Vora | fix(server): correct CORS response header list length | Server / proxy hardening | 1 | 1 | 1 | Server/proxy backend (1) | Stability, bug fix, or maintenance work.
2026-05-08 15:12:13 ET | a97c34b | Bhaskar Vora | fix: address recent stability and model hub issues | Startup / provider readiness | 479 | 171 | 28 | Web app libraries (7), UI components (6), Tests (3) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 15:15:51 ET | ba2e562 | Bhaskar Vora | fix(core): align fallback events bridge typing | General stability | 9 | 6 | 1 | Core package (1) | Stability, bug fix, or maintenance work.
2026-05-08 16:47:50 ET | bb9bbc2 | Bhaskar Vora | fix local knowledge and startup stability | Local knowledge / MCP | 578 | 103 | 16 | Thread/chat hooks (5), Web app libraries (3), Server/proxy backend (2) | Improved local knowledge retrieval, MCP resilience, and result handling.
2026-05-08 18:30:16 ET | 82c734e | Bhaskar Vora | Fix local knowledge retrieval and startup behavior | Local knowledge / MCP | 642 | 494 | 33 | Web app libraries (5), Server/proxy backend (4), Other (4) | Improved local knowledge retrieval, MCP resilience, and result handling.
2026-05-08 19:46:43 ET | 30749b8 | Bhaskar Vora | Stabilize local knowledge and MCP flows | Local knowledge / MCP | 875 | 58 | 19 | Tests (5), Thread/chat hooks (3), Web app libraries (3) | Improved local knowledge retrieval, MCP resilience, and result handling.
2026-05-08 19:55:35 ET | b507716 | Bhaskar Vora | Add native storage fallback for conversations | Thread and conversation storage | 399 | 167 | 4 | Tests (2), Web services (2) | Stability, bug fix, or maintenance work.
2026-05-08 20:59:33 ET | 15c29ea | Bhaskar Vora | fix chat startup and stability regressions | Local knowledge / MCP | 1170 | 404 | 33 | Tests (11), Web services (4), UI components (3) | Improved local knowledge retrieval, MCP resilience, and result handling.
2026-05-08 21:05:39 ET | ae7097d | Bhaskar Vora | chore: tighten stability cleanup coverage | Local knowledge / MCP | 30 | 22 | 11 | Tests (3), Tauri backend (2), UI components (2) | Improved local knowledge retrieval, MCP resilience, and result handling.
2026-05-08 21:45:06 ET | 16ba001 | Bhaskar Vora | Stabilize chat startup tools and quality coverage | Startup / provider readiness | 731 | 259 | 37 | Tests (13), UI components (11), Web app libraries (5) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-08 22:17:56 ET | c735ea6 | Bhaskar Vora | Harden quality tests and update reports | Local knowledge / MCP | 744 | 106 | 42 | Tests (40), Docs/reports (2) | Improved local knowledge retrieval, MCP resilience, and result handling.
2026-05-09 16:33:41 ET | c321409 | Bhaskar Vora | Improve local inference readiness and stability | Startup / provider readiness | 1325 | 139 | 23 | Tests (7), App providers (3), Docs/reports (2) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-09 16:41:48 ET | f3cc955 | Bhaskar Vora | Wait for local model startup before streaming | Startup / provider readiness | 60 | 29 | 2 | Tests (1), Web app libraries (1) | Improved startup sequencing, provider discovery, or readiness behavior.
2026-05-09 16:55:04 ET | 197abef | Bhaskar Vora | Avoid local chat startup deadlock | Startup / provider readiness | 58 | 20 | 2 | Tests (1), Web app libraries (1) | Improved startup sequencing, provider discovery, or readiness behavior.

## File Changes
Date | Hash | Commit Subject | Area | File | Additions | Deletions | Net
2026-05-08 | e26fba4 | refactor: clean up thread storage handling and flag reads | UI components | web-app/src/containers/threads/MessagesArea.tsx | 7 | 11 | -4
2026-05-08 | e26fba4 | refactor: clean up thread storage handling and flag reads | Thread/chat hooks | web-app/src/hooks/threads/use-thread-effects.ts | 20 | 26 | -6
2026-05-08 | e26fba4 | refactor: clean up thread storage handling and flag reads | Web app libraries | web-app/src/lib/storage/storage.ts | 59 | 14 | 45
2026-05-08 | e26fba4 | refactor: clean up thread storage handling and flag reads | Other | web-app/src/routes/index.tsx | 8 | 6 | 2
2026-05-08 | 44bc411 | fix(core): return owned finish_reason string to satisfy lifetimes | Server/proxy backend | src-tauri/src/core/server/provider_adapter.rs | 28 | 35 | -7
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Docs/reports | docs/AX-Studio-Stability-Report-2026-05-07.html | 571 | 0 | 571
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Tests | web-app/src/lib/__tests__/huggingface.test.ts | 16 | 0 | 16
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Web app libraries | web-app/src/lib/bootstrap/bootstrap-utils.ts | 43 | 0 | 43
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Web app libraries | web-app/src/lib/huggingface.ts | 24 | 0 | 24
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Web app libraries | web-app/src/lib/utils/async.ts | 17 | 0 | 17
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Web app libraries | web-app/src/lib/utils/download.ts | 19 | 0 | 19
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Web app libraries | web-app/src/lib/utils/json.ts | 31 | 0 | 31
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Web app libraries | web-app/src/lib/utils/local-provider.ts | 76 | 0 | 76
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Model hub | web-app/src/routes/hub/-hubFilters.ts | 11 | 0 | 11
2026-05-08 | c189427 | chore: add local workspace files pending from sync | Tests | web-app/src/routes/hub/__tests__/hubFilters.test.ts | 60 | 0 | 60
2026-05-08 | f35d74e | Add timeout to extension startup path | App providers | web-app/src/providers/ExtensionProvider.tsx | 9 | 3 | 6
2026-05-08 | 663f3eb | Harden provider discovery and registration with bounded timeouts | Web app libraries | web-app/src/lib/providers/provider-sync.ts | 23 | 3 | 20
2026-05-08 | 663f3eb | Harden provider discovery and registration with bounded timeouts | Web services | web-app/src/services/providers/tauri.ts | 139 | 81 | 58
2026-05-08 | f40646b | fix: stabilize startup event bridge and context-size error handling | Docs/reports | web-app/index.html | 12 | 0 | 12
2026-05-08 | f40646b | fix: stabilize startup event bridge and context-size error handling | Web app libraries | web-app/src/lib/bootstrap/bootstrap-providers.ts | 55 | 41 | 14
2026-05-08 | f40646b | fix: stabilize startup event bridge and context-size error handling | Web app libraries | web-app/src/lib/extension.ts | 14 | 6 | 8
2026-05-08 | f40646b | fix: stabilize startup event bridge and context-size error handling | Web app libraries | web-app/src/lib/utils/error.ts | 22 | 0 | 22
2026-05-08 | f40646b | fix: stabilize startup event bridge and context-size error handling | Other | web-app/src/main.tsx | 22 | 0 | 22
2026-05-08 | f40646b | fix: stabilize startup event bridge and context-size error handling | App providers | web-app/src/providers/ExtensionProvider.tsx | 5 | 6 | -1
2026-05-08 | f40646b | fix: stabilize startup event bridge and context-size error handling | App providers | web-app/src/providers/ServiceHubProvider.tsx | 37 | 4 | 33
2026-05-08 | 6888db8 | Fix local MLX model discovery in Ax Studio | Tests | extensions/llamacpp-extension/src/index.test.ts | 58 | 0 | 58
2026-05-08 | 6888db8 | Fix local MLX model discovery in Ax Studio | Llamacpp extension | extensions/llamacpp-extension/src/index.ts | 19 | 3 | 16
2026-05-08 | 6888db8 | Fix local MLX model discovery in Ax Studio | Tauri backend | src-tauri/src/core/setup.rs | 19 | 7 | 12
2026-05-08 | e686922 | Show MLX filter in model hub | Model hub | web-app/src/routes/hub/index.tsx | 11 | 3 | 8
2026-05-08 | ca2b39e | fix: encode hub model ids and normalize HF links | App providers | web-app/src/providers/DataProvider.tsx | 1 | 1 | 0
2026-05-08 | ca2b39e | fix: encode hub model ids and normalize HF links | Model hub | web-app/src/routes/hub/$modelId.tsx | 67 | 14 | 53
2026-05-08 | ca2b39e | fix: encode hub model ids and normalize HF links | Model hub | web-app/src/routes/hub/index.tsx | 1 | 1 | 0
2026-05-08 | cfac31b | refactor: centralize hub model routing and HF link parsing | Web app libraries | web-app/src/lib/hub.ts | 50 | 0 | 50
2026-05-08 | cfac31b | refactor: centralize hub model routing and HF link parsing | App providers | web-app/src/providers/DataProvider.tsx | 2 | 1 | 1
2026-05-08 | cfac31b | refactor: centralize hub model routing and HF link parsing | Model hub | web-app/src/routes/hub/$modelId.tsx | 13 | 43 | -30
2026-05-08 | cfac31b | refactor: centralize hub model routing and HF link parsing | Model hub | web-app/src/routes/hub/index.tsx | 2 | 1 | 1
2026-05-08 | 9c2d47a | refactor(web-app): consolidate Hugging Face URL helpers | UI components | web-app/src/containers/DownloadButton.tsx | 2 | 1 | 1
2026-05-08 | 9c2d47a | refactor(web-app): consolidate Hugging Face URL helpers | Tests | web-app/src/lib/__tests__/huggingface.test.ts | 32 | 1 | 31
2026-05-08 | 9c2d47a | refactor(web-app): consolidate Hugging Face URL helpers | Web app libraries | web-app/src/lib/huggingface.ts | 21 | 0 | 21
2026-05-08 | 9c2d47a | refactor(web-app): consolidate Hugging Face URL helpers | Web services | web-app/src/services/models/default.ts | 32 | 20 | 12
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri llamacpp plugin | src-tauri/plugins/tauri-plugin-llamacpp/src/backend.rs | 12 | 3 | 9
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri llamacpp plugin | src-tauri/plugins/tauri-plugin-llamacpp/src/cleanup.rs | 4 | 1 | 3
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri llamacpp plugin | src-tauri/plugins/tauri-plugin-llamacpp/src/commands.rs | 43 | 9 | 34
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri llamacpp plugin | src-tauri/plugins/tauri-plugin-llamacpp/src/device.rs | 3 | 1 | 2
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri llamacpp plugin | src-tauri/plugins/tauri-plugin-llamacpp/src/gguf/commands.rs | 13 | 3 | 10
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri llamacpp plugin | src-tauri/plugins/tauri-plugin-llamacpp/src/gguf/types.rs | 0 | 1 | -1
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri backend | src-tauri/src/core/filesystem/tests.rs | 4 | 2 | 2
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | MCP backend | src-tauri/src/core/mcp/commands.rs | 6 | 10 | -4
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | MCP backend | src-tauri/src/core/mcp/helpers.rs | 33 | 25 | 8
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | MCP backend | src-tauri/src/core/mcp/lockfile.rs | 10 | 2 | 8
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri backend | src-tauri/src/core/research/scraper.rs | 9 | 9 | 0
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Server/proxy backend | src-tauri/src/core/server/gateway_routes.rs | 1 | 1 | 0
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 44 | 24 | 20
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Server/proxy backend | src-tauri/src/core/server/provider_adapter.rs | 1 | 1 | 0
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Server/proxy backend | src-tauri/src/core/server/proxy.rs | 17 | 12 | 5
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri backend | src-tauri/src/core/system/commands.rs | 23 | 7 | 16
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Tauri backend | src-tauri/src/core/threads/tests.rs | 0 | 1 | -1
2026-05-08 | aaebeda | chore(core): apply remaining refactor and cleanup changes | Other | src-tauri/utils/src/crypto.rs | 20 | 18 | 2
2026-05-08 | de7fc77 | refactor(server,huggingface): centralize URL cleanup and endpoint suffix stripping | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 12 | 10 | 2
2026-05-08 | de7fc77 | refactor(server,huggingface): centralize URL cleanup and endpoint suffix stripping | Tests | web-app/src/lib/__tests__/hub.test.ts | 42 | 0 | 42
2026-05-08 | de7fc77 | refactor(server,huggingface): centralize URL cleanup and endpoint suffix stripping | Web app libraries | web-app/src/lib/hub.ts | 6 | 9 | -3
2026-05-08 | 5954ed8 | refactor(server,tests): centralize upstream-header filtering and reuse hf URL helper in tests | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 23 | 13 | 10
2026-05-08 | 5954ed8 | refactor(server,tests): centralize upstream-header filtering and reuse hf URL helper in tests | Tests | web-app/src/routes/hub/__tests__/huggingface-conversion.test.ts | 10 | 9 | 1
2026-05-08 | 6bcf1d2 | refactor(web): centralize core bridge initialization | Web app libraries | web-app/src/lib/bootstrap/core-bridge.ts | 21 | 0 | 21
2026-05-08 | 6bcf1d2 | refactor(web): centralize core bridge initialization | Web app libraries | web-app/src/lib/extension.ts | 5 | 15 | -10
2026-05-08 | 6bcf1d2 | refactor(web): centralize core bridge initialization | Other | web-app/src/main.tsx | 2 | 12 | -10
2026-05-08 | 6bcf1d2 | refactor(web): centralize core bridge initialization | App providers | web-app/src/providers/ExtensionProvider.tsx | 5 | 11 | -6
2026-05-08 | bad4a8e | refactor(server): centralize CORS constants | Server/proxy backend | src-tauri/src/core/server/cors.rs | 70 | 0 | 70
2026-05-08 | bad4a8e | refactor(server): centralize CORS constants | Server/proxy backend | src-tauri/src/core/server/mod.rs | 1 | 0 | 1
2026-05-08 | bad4a8e | refactor(server): centralize CORS constants | Server/proxy backend | src-tauri/src/core/server/proxy.rs | 11 | 34 | -23
2026-05-08 | bad4a8e | refactor(server): centralize CORS constants | Server/proxy backend | src-tauri/src/core/server/security.rs | 6 | 2 | 4
2026-05-08 | bad4a8e | refactor(server): centralize CORS constants | Server/proxy backend | src-tauri/src/core/server/tests.rs | 3 | 42 | -39
2026-05-08 | 0ba1f97 | fix(server): correct CORS response header list length | Server/proxy backend | src-tauri/src/core/server/cors.rs | 1 | 1 | 0
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Core package | core/src/browser/events.ts | 33 | 12 | 21
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Tauri backend | src-tauri/src/core/extensions/commands.rs | 8 | 2 | 6
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Server/proxy backend | src-tauri/src/core/server/tests.rs | 4 | 4 | 0
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Tauri backend | src-tauri/src/core/setup.rs | 88 | 23 | 65
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | UI components | web-app/src/components/TokenCounter.tsx | 4 | 1 | 3
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | UI components | web-app/src/containers/ChatInput.tsx | 10 | 2 | 8
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | UI components | web-app/src/containers/DownloadButton.tsx | 19 | 22 | -3
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | UI components | web-app/src/containers/MessageItem.tsx | 28 | 0 | 28
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | UI components | web-app/src/containers/ModelDownloadAction.tsx | 17 | 27 | -10
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Tests | web-app/src/containers/__tests__/DownloadButton.test.tsx | 14 | 11 | 3
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Tests | web-app/src/containers/__tests__/ModelDownloadAction.test.tsx | 4 | 1 | 3
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | UI components | web-app/src/containers/dialogs/thread/DeleteThreadDialog.tsx | 6 | 2 | 4
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Chat hooks | web-app/src/hooks/chat/use-chat.ts | 15 | 1 | 14
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Chat hooks | web-app/src/hooks/chat/useTokensCount.ts | 4 | 2 | 2
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Thread/chat hooks | web-app/src/hooks/threads/use-thread-chat.ts | 10 | 5 | 5
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Tests | web-app/src/lib/__tests__/huggingface.test.ts | 3 | 3 | 0
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web app libraries | web-app/src/lib/chat/chat-transport-factory.ts | 3 | 1 | 2
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web app libraries | web-app/src/lib/custom-chat-transport.ts | 15 | 3 | 12
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web app libraries | web-app/src/lib/extension.ts | 8 | 1 | 7
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web app libraries | web-app/src/lib/huggingface.ts | 1 | 1 | 0
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web app libraries | web-app/src/lib/messages/index.ts | 30 | 3 | 27
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web app libraries | web-app/src/lib/models/downloaded.ts | 71 | 0 | 71
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web app libraries | web-app/src/lib/transport/single-agent-transport.ts | 27 | 0 | 27
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Model hub | web-app/src/routes/hub/$modelId.tsx | 15 | 13 | 2
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Model hub | web-app/src/routes/hub/index.tsx | 16 | 22 | -6
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Other | web-app/src/routes/threads/$threadId.tsx | 15 | 2 | 13
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web services | web-app/src/services/models/default.ts | 6 | 6 | 0
2026-05-08 | a97c34b | fix: address recent stability and model hub issues | Web services | web-app/src/services/providers/tauri.ts | 5 | 1 | 4
2026-05-08 | ba2e562 | fix(core): align fallback events bridge typing | Core package | core/src/browser/events.ts | 9 | 6 | 3
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Llamacpp extension | extensions/llamacpp-extension/src/index.ts | 22 | 2 | 20
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Config/build | extensions/yarn.lock | 8 | 8 | 0
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Tauri backend | src-tauri/src/core/extensions/commands.rs | 19 | 8 | 11
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 88 | 21 | 67
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Server/proxy backend | src-tauri/src/core/server/provider_adapter.rs | 32 | 0 | 32
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Thread/chat hooks | web-app/src/hooks/threads/use-thread-chat.ts | 5 | 1 | 4
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Thread/chat hooks | web-app/src/hooks/threads/use-thread-local-knowledge.ts | 85 | 5 | 80
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Thread/chat hooks | web-app/src/hooks/threads/use-thread-research.ts | 2 | 1 | 1
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Thread/chat hooks | web-app/src/hooks/threads/use-thread-tools.ts | 119 | 1 | 118
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Thread/chat hooks | web-app/src/hooks/threads/useThreads.ts | 12 | 4 | 8
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Web app libraries | web-app/src/lib/extension.ts | 1 | 1 | 0
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Web app libraries | web-app/src/lib/model-factory.ts | 83 | 6 | 77
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Web app libraries | web-app/src/lib/prompts/system-prompt.ts | 1 | 1 | 0
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | App providers | web-app/src/providers/ServiceHubProvider.tsx | 8 | 1 | 7
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Web services | web-app/src/services/messages/default.ts | 38 | 20 | 18
2026-05-08 | bb9bbc2 | fix local knowledge and startup stability | Web services | web-app/src/services/threads/default.ts | 55 | 23 | 32
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Config/build | .mcp.json | 2 | 2 | 0
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Tauri backend | src-tauri/src/core/extensions/commands.rs | 44 | 25 | 19
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Tauri backend | src-tauri/src/core/filesystem/akidb.rs | 4 | 4 | 0
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | MCP backend | src-tauri/src/core/mcp/commands.rs | 28 | 11 | 17
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | MCP backend | src-tauri/src/core/mcp/constants.rs | 1 | 1 | 0
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | MCP backend | src-tauri/src/core/mcp/helpers.rs | 42 | 17 | 25
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Server/proxy backend | src-tauri/src/core/server/cors.rs | 0 | 23 | -23
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 80 | 43 | 37
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Server/proxy backend | src-tauri/src/core/server/proxy.rs | 1 | 8 | -7
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Server/proxy backend | src-tauri/src/core/server/remote_provider_commands.rs | 24 | 4 | 20
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Tauri backend | src-tauri/src/core/setup.rs | 37 | 7 | 30
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Other | src-tauri/utils/src/network.rs | 4 | 0 | 4
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | UI components | web-app/src/components/ai-elements/code-block.tsx | 13 | 5 | 8
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Chat hooks | web-app/src/hooks/chat/use-chat.ts | 3 | 2 | 1
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Chat hooks | web-app/src/hooks/chat/use-image-attachment-handler.ts | 10 | 0 | 10
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Chat hooks | web-app/src/hooks/chat/useTokensCount.ts | 2 | 1 | 1
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Tests | web-app/src/hooks/research/__tests__/useAkidbConfig.test.ts | 1 | 1 | 0
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Other | web-app/src/hooks/research/useAkidbConfig.ts | 1 | 1 | 0
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Tests | web-app/src/hooks/threads/__tests__/use-thread-local-knowledge.test.ts | 5 | 92 | -87
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Thread/chat hooks | web-app/src/hooks/threads/use-thread-chat.ts | 11 | 1 | 10
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Thread/chat hooks | web-app/src/hooks/threads/use-thread-local-knowledge.ts | 3 | 157 | -154
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Thread/chat hooks | web-app/src/hooks/threads/use-thread-tools.ts | 204 | 7 | 197
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Web app libraries | web-app/src/lib/model-factory.ts | 1 | 8 | -7
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Web app libraries | web-app/src/lib/prompts/system-prompt.ts | 2 | 7 | -5
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Web app libraries | web-app/src/lib/research/research-scraper.ts | 17 | 3 | 14
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Web app libraries | web-app/src/lib/research/research-search.ts | 2 | 2 | 0
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Web app libraries | web-app/src/lib/storage/crypto.ts | 7 | 47 | -40
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Tests | web-app/src/providers/__tests__/ServiceHubProvider.test.tsx | 3 | 2 | 1
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Model hub | web-app/src/routes/hub/$modelId.tsx | 17 | 5 | 12
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Other | web-app/src/routes/settings/mcp-servers.tsx | 1 | 1 | 0
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Other | web-app/src/routes/threads/$threadId.tsx | 3 | 0 | 3
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Web services | web-app/src/services/index.ts | 31 | 3 | 28
2026-05-08 | 82c734e | Fix local knowledge retrieval and startup behavior | Web services | web-app/src/services/providers/tauri.ts | 38 | 4 | 34
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | MCP backend | src-tauri/src/core/mcp/commands.rs | 68 | 4 | 64
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Server/proxy backend | src-tauri/src/core/server/cors.rs | 26 | 0 | 26
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 33 | 5 | 28
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | UI components | web-app/src/containers/MessageItem.tsx | 25 | 1 | 24
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Tests | web-app/src/containers/__tests__/MessageItem.test.tsx | 25 | 0 | 25
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Tests | web-app/src/hooks/threads/__tests__/use-thread-chat.test.ts | 72 | 0 | 72
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Tests | web-app/src/hooks/threads/__tests__/use-thread-local-knowledge.test.ts | 96 | 7 | 89
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Thread/chat hooks | web-app/src/hooks/threads/use-thread-chat.ts | 54 | 8 | 46
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Thread/chat hooks | web-app/src/hooks/threads/use-thread-local-knowledge.ts | 297 | 3 | 294
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Thread/chat hooks | web-app/src/hooks/threads/use-thread-tools.ts | 13 | 8 | 5
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Web app libraries | web-app/src/lib/model-factory.ts | 16 | 1 | 15
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Tests | web-app/src/lib/prompts/__tests__/system-prompt.test.ts | 10 | 0 | 10
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Web app libraries | web-app/src/lib/prompts/system-prompt.ts | 7 | 5 | 2
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Web app libraries | web-app/src/lib/research/research-search.ts | 22 | 2 | 20
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Other | web-app/src/routes/logs.tsx | 11 | 1 | 10
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Other | web-app/src/routes/settings/hardware.tsx | 10 | 4 | 6
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Other | web-app/src/routes/system-monitor.tsx | 11 | 4 | 7
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Tests | web-app/src/services/__tests__/mcp.test.ts | 33 | 2 | 31
2026-05-08 | 30749b8 | Stabilize local knowledge and MCP flows | Web services | web-app/src/services/mcp/tauri.ts | 46 | 3 | 43
2026-05-08 | b507716 | Add native storage fallback for conversations | Tests | web-app/src/services/__tests__/messages.test.ts | 98 | 7 | 91
2026-05-08 | b507716 | Add native storage fallback for conversations | Tests | web-app/src/services/__tests__/threads.test.ts | 56 | 6 | 50
2026-05-08 | b507716 | Add native storage fallback for conversations | Web services | web-app/src/services/messages/default.ts | 110 | 78 | 32
2026-05-08 | b507716 | Add native storage fallback for conversations | Web services | web-app/src/services/threads/default.ts | 135 | 76 | 59
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Docs/reports | app-stability-cleanliness-test-report.html | 440 | 0 | 440
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | core/src/browser/events.test.ts | 13 | 12 | 1
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Llamacpp extension | extensions/llamacpp-extension/src/index.ts | 2 | 0 | 2
2026-05-08 | 15c29ea | fix chat startup and stability regressions | MCP backend | src-tauri/src/core/mcp/commands.rs | 127 | 26 | 101
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 16 | 0 | 16
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tauri backend | src-tauri/src/core/setup.rs | 81 | 8 | 73
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Config/build | src-tauri/tauri.conf.json | 27 | 0 | 27
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Docs/reports | web-app/index.html | 1 | 1 | 0
2026-05-08 | 15c29ea | fix chat startup and stability regressions | UI components | web-app/src/components/chat/ChatInputToolbar.tsx | 10 | 2 | 8
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/components/chat/__tests__/ChatInputToolbar.test.tsx | 4 | 3 | 1
2026-05-08 | 15c29ea | fix chat startup and stability regressions | UI components | web-app/src/containers/ChatInput.tsx | 10 | 2 | 8
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/containers/__tests__/ChatInput.phase3.test.tsx | 12 | 2 | 10
2026-05-08 | 15c29ea | fix chat startup and stability regressions | UI components | web-app/src/containers/threads/MessagesArea.tsx | 5 | 5 | 0
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/hooks/chat/__tests__/use-chat-send-handler.test.ts | 13 | 3 | 10
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/hooks/chat/__tests__/use-chat.test.ts | 2 | 0 | 2
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Chat hooks | web-app/src/hooks/chat/use-chat-send-handler.ts | 16 | 4 | 12
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/hooks/threads/__tests__/use-thread-effects.test.ts | 54 | 2 | 52
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Thread/chat hooks | web-app/src/hooks/threads/use-thread-effects.ts | 24 | 5 | 19
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/lib/__tests__/extension.test.ts | 3 | 0 | 3
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/lib/__tests__/model-factory.test.ts | 19 | 2 | 17
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Web app libraries | web-app/src/lib/bootstrap/bootstrap-local-api.ts | 1 | 1 | 0
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/lib/chat/__tests__/chat-transport-factory.test.ts | 3 | 1 | 2
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Web app libraries | web-app/src/lib/hub.ts | 8 | 17 | -9
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Web app libraries | web-app/src/lib/model-factory.ts | 14 | 0 | 14
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Other | web-app/src/main.tsx | 10 | 13 | -3
2026-05-08 | 15c29ea | fix chat startup and stability regressions | App providers | web-app/src/providers/ExtensionProvider.tsx | 33 | 1 | 32
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/services/__tests__/models.test.ts | 6 | 6 | 0
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Tests | web-app/src/services/__tests__/providers-tauri.test.ts | 7 | 7 | 0
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Web services | web-app/src/services/conversation-storage.ts | 48 | 0 | 48
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Web services | web-app/src/services/messages/default.ts | 56 | 110 | -54
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Web services | web-app/src/services/threads/default.ts | 97 | 170 | -73
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Web services | web-app/src/services/updater/tauri.ts | 1 | 1 | 0
2026-05-08 | 15c29ea | fix chat startup and stability regressions | Config/build | web-app/vite.config.ts | 7 | 0 | 7
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Tests | extensions/llamacpp-extension/src/index.test.ts | 3 | 0 | 3
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Tauri backend | src-tauri/src/core/filesystem/tests.rs | 0 | 1 | -1
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | MCP backend | src-tauri/src/core/mcp/tests.rs | 0 | 1 | -1
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Server/proxy backend | src-tauri/src/core/server/commands.rs | 0 | 1 | -1
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Tauri backend | src-tauri/src/core/state.rs | 0 | 2 | -2
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Other | src-tauri/src/lib.rs | 0 | 2 | -2
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Tests | web-app/src/__tests__/main.test.tsx | 4 | 3 | 1
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | UI components | web-app/src/components/chat/ChatInputToolbar.tsx | 3 | 4 | -1
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | UI components | web-app/src/containers/threads/MessagesArea.tsx | 2 | 3 | -1
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Tests | web-app/src/services/__tests__/hardware.test.ts | 8 | 0 | 8
2026-05-08 | ae7097d | chore: tighten stability cleanup coverage | Web services | web-app/src/services/hardware/tauri.ts | 10 | 5 | 5
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Docs/reports | app-stability-cleanliness-test-report.html | 160 | 34 | 126
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Assistant extension | extensions/assistant-extension/src/index.ts | 11 | 6 | 5
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tauri backend | src-tauri/src/core/setup.rs | 66 | 91 | -25
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/components/WindowControls.tsx | 17 | 6 | 11
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/components/__tests__/LogViewer.test.tsx | 16 | 10 | 6
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/components/__tests__/WindowControls.test.tsx | 19 | 1 | 18
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/components/chat/ChatInputToolbar.tsx | 11 | 4 | 7
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/components/chat/__tests__/ChatInputToolbar.test.tsx | 26 | 1 | 25
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/components/ui/__tests__/dialog.test.tsx | 18 | 4 | 14
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/components/ui/__tests__/hover-card.test.tsx | 3 | 3 | 0
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/components/ui/command.tsx | 8 | 1 | 7
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/components/ui/sidebar.tsx | 8 | 1 | 7
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/containers/ChatInput.tsx | 9 | 7 | 2
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/containers/DropdownModelProvider.tsx | 10 | 4 | 6
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/containers/MessageItem.tsx | 42 | 20 | 22
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/containers/RenderMarkdown.tsx | 10 | 8 | 2
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/containers/__tests__/ChatInput.phase3.test.tsx | 49 | 0 | 49
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/containers/dialogs/model/DeleteModel.tsx | 1 | 4 | -3
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/containers/threads/SplitThreadContainer.tsx | 2 | 2 | 0
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | UI components | web-app/src/containers/threads/ThreadView.tsx | 2 | 2 | 0
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/hooks/chat/__tests__/useAssistant.test.ts | 5 | 1 | 4
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/hooks/chat/__tests__/useMessages.test.ts | 30 | 11 | 19
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/hooks/settings/__tests__/useLocalApiServer.test.ts | 4 | 1 | 3
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Thread/chat hooks | web-app/src/hooks/threads/use-thread-tools.ts | 1 | 2 | -1
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Other | web-app/src/hooks/updater/useBackendUpdater.ts | 5 | 4 | 1
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Other | web-app/src/hooks/updater/useReleaseNotes.ts | 13 | 9 | 4
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/lib/__tests__/memory-extractor.test.ts | 7 | 1 | 6
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/lib/chat/__tests__/selected-model.test.ts | 65 | 0 | 65
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Web app libraries | web-app/src/lib/chat/chat-session-controller.ts | 7 | 3 | 4
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Web app libraries | web-app/src/lib/chat/chat-session-types.ts | 1 | 2 | -1
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Web app libraries | web-app/src/lib/chat/selected-model.ts | 33 | 0 | 33
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Web app libraries | web-app/src/lib/completion.ts | 3 | 3 | 0
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Web app libraries | web-app/src/lib/messages/index.ts | 35 | 4 | 31
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/lib/utils/__tests__/getModelToStart.test.ts | 15 | 1 | 14
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Tests | web-app/src/providers/__tests__/ServiceHubProvider.test.tsx | 14 | 1 | 13
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Other | web-app/src/routes/settings/llm-router.tsx | 1 | 2 | -1
2026-05-08 | 16ba001 | Stabilize chat startup tools and quality coverage | Other | web-app/src/types/global.d.ts | 4 | 5 | -1
2026-05-08 | c735ea6 | Harden quality tests and update reports | Docs/reports | app-stability-cleanliness-test-report.html | 35 | 27 | 8
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | core/src/browser/extension.test.ts | 13 | 0 | 13
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | core/src/browser/extensions/engines/LocalOAIEngine.test.ts | 10 | 1 | 9
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | core/src/browser/extensions/engines/OAIEngine.test.ts | 11 | 5 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | core/src/browser/models/manager.test.ts | 1 | 0 | 1
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | extensions/llamacpp-extension/src/backend.test.ts | 15 | 1 | 14
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | extensions/llamacpp-extension/src/index.test.ts | 17 | 1 | 16
2026-05-08 | c735ea6 | Harden quality tests and update reports | Docs/reports | manager-quality-summary.html | 324 | 0 | 324
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/__tests__/main.test.tsx | 6 | 0 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/components/common/__tests__/GlobalError.test.tsx | 11 | 4 | 7
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/containers/__tests__/DownloadButton.test.tsx | 7 | 1 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/containers/__tests__/ModelDownloadAction.test.tsx | 6 | 0 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/chat/__tests__/use-chat-send-handler.test.ts | 11 | 1 | 10
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/chat/__tests__/use-document-attachment-handler.test.ts | 10 | 1 | 9
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/chat/__tests__/use-image-attachment-handler.test.ts | 12 | 4 | 8
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/models/__tests__/useLlamacppDevices.test.ts | 8 | 1 | 7
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/models/__tests__/useModelContextApproval.test.ts | 7 | 5 | 2
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/threads/__tests__/use-thread-effects.test.ts | 7 | 1 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/threads/__tests__/use-thread-memory.test.ts | 4 | 1 | 3
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/threads/__tests__/useThreads.test.ts | 4 | 1 | 3
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/tools/__tests__/useToolApproval.test.ts | 9 | 7 | 2
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/hooks/updater/__tests__/useBackendUpdater.test.ts | 8 | 13 | -5
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/lib/__tests__/attachmentProcessing.test.ts | 14 | 1 | 13
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/lib/__tests__/custom-chat-transport.test.ts | 11 | 1 | 10
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/lib/bootstrap/__tests__/bootstrap-local-api.test.ts | 11 | 1 | 10
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/lib/bootstrap/__tests__/bootstrap-providers.test.ts | 11 | 1 | 10
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/lib/bootstrap/__tests__/bootstrap-threads.test.ts | 6 | 1 | 5
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/lib/chat/__tests__/chat-session-controller.test.ts | 11 | 1 | 10
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/lib/research/__tests__/research-scraper.test.ts | 11 | 1 | 10
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/assistants.test.ts | 11 | 6 | 5
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/hardware.test.ts | 12 | 7 | 5
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/mcp-activation.test.ts | 7 | 1 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/mcp.test.ts | 10 | 1 | 9
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/messages.test.ts | 7 | 1 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/models.test.ts | 31 | 1 | 30
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/path.test.ts | 7 | 1 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/providers-tauri.test.ts | 5 | 0 | 5
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/rag-default.test.ts | 10 | 1 | 9
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/threads.test.ts | 10 | 1 | 9
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/updater-tauri.test.ts | 8 | 2 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/services/__tests__/uploads-default.test.ts | 7 | 1 | 6
2026-05-08 | c735ea6 | Harden quality tests and update reports | Tests | web-app/src/stores/__tests__/chat-session-store.test.ts | 8 | 1 | 7
2026-05-09 | c321409 | Improve local inference readiness and stability | Docs/reports | app-stability-cleanliness-test-report.html | 8 | 7 | 1
2026-05-09 | c321409 | Improve local inference readiness and stability | Llamacpp extension | extensions/llamacpp-extension/settings.json | 1 | 1 | 0
2026-05-09 | c321409 | Improve local inference readiness and stability | Llamacpp extension | extensions/llamacpp-extension/src/index.ts | 17 | 0 | 17
2026-05-09 | c321409 | Improve local inference readiness and stability | Docs/reports | manager-quality-summary.html | 8 | 7 | 1
2026-05-09 | c321409 | Improve local inference readiness and stability | Tauri backend | src-tauri/src/core/extensions/commands.rs | 11 | 9 | 2
2026-05-09 | c321409 | Improve local inference readiness and stability | Server/proxy backend | src-tauri/src/core/server/model_routes.rs | 70 | 0 | 70
2026-05-09 | c321409 | Improve local inference readiness and stability | Tauri backend | src-tauri/src/core/setup.rs | 73 | 3 | 70
2026-05-09 | c321409 | Improve local inference readiness and stability | UI components | web-app/src/containers/DynamicControllerSetting.tsx | 16 | 21 | -5
2026-05-09 | c321409 | Improve local inference readiness and stability | Tests | web-app/src/lib/__tests__/custom-chat-transport.test.ts | 100 | 4 | 96
2026-05-09 | c321409 | Improve local inference readiness and stability | Web app libraries | web-app/src/lib/bootstrap/bootstrap-providers.ts | 44 | 9 | 35
2026-05-09 | c321409 | Improve local inference readiness and stability | Web app libraries | web-app/src/lib/custom-chat-transport.ts | 184 | 5 | 179
2026-05-09 | c321409 | Improve local inference readiness and stability | App providers | web-app/src/providers/ExtensionProvider.tsx | 71 | 37 | 34
2026-05-09 | c321409 | Improve local inference readiness and stability | App providers | web-app/src/providers/GlobalEventHandler.tsx | 2 | 2 | 0
2026-05-09 | c321409 | Improve local inference readiness and stability | App providers | web-app/src/providers/ServiceHubProvider.tsx | 4 | 4 | 0
2026-05-09 | c321409 | Improve local inference readiness and stability | Tests | web-app/src/providers/__tests__/ExtensionProvider.test.tsx | 145 | 0 | 145
2026-05-09 | c321409 | Improve local inference readiness and stability | Tests | web-app/src/providers/__tests__/ServiceHubProvider.test.tsx | 16 | 14 | 2
2026-05-09 | c321409 | Improve local inference readiness and stability | Tests | web-app/src/routes/__tests__/utility-pages.test.tsx | 184 | 0 | 184
2026-05-09 | c321409 | Improve local inference readiness and stability | Tests | web-app/src/routes/settings/__tests__/settings-extra-pages.test.tsx | 294 | 0 | 294
2026-05-09 | c321409 | Improve local inference readiness and stability | Other | web-app/src/routes/settings/engine-settings.tsx | 36 | 6 | 30
2026-05-09 | c321409 | Improve local inference readiness and stability | Tests | web-app/src/services/__tests__/models.test.ts | 1 | 1 | 0
2026-05-09 | c321409 | Improve local inference readiness and stability | Tests | web-app/src/services/__tests__/serviceHub.integration.test.ts | 4 | 4 | 0
2026-05-09 | c321409 | Improve local inference readiness and stability | Web services | web-app/src/services/index.ts | 16 | 3 | 13
2026-05-09 | c321409 | Improve local inference readiness and stability | Web services | web-app/src/services/models/default.ts | 20 | 2 | 18
2026-05-09 | f3cc955 | Wait for local model startup before streaming | Tests | web-app/src/lib/__tests__/custom-chat-transport.test.ts | 59 | 0 | 59
2026-05-09 | f3cc955 | Wait for local model startup before streaming | Web app libraries | web-app/src/lib/custom-chat-transport.ts | 1 | 29 | -28
2026-05-09 | 197abef | Avoid local chat startup deadlock | Tests | web-app/src/lib/__tests__/custom-chat-transport.test.ts | 14 | 8 | 6
2026-05-09 | 197abef | Avoid local chat startup deadlock | Web app libraries | web-app/src/lib/custom-chat-transport.ts | 44 | 12 | 32

## Refactoring Themes
Theme | Commits | Additions | Deletions | Files Changed | Impact / Reason | Representative Commits
Startup / provider readiness | 13 | 4056 | 896 | 124 | Reduced blank startup states and bounded provider/model readiness waits. | 44bc411: fix(core): return owned finish_reason string to satisfy lifetimes c189427: chore: add local workspace files pending from sync f35d74e: Add timeout to extension startup path 663f3eb: Harden provider discovery and registration with bounded timeouts f40646b: fix: stabilize startup event bridge and context-size error handling
Local knowledge / MCP | 7 | 4282 | 1317 | 172 | More reliable local knowledge retrieval, MCP retry/restart behavior, and hidden context injection. | aaebeda: chore(core): apply remaining refactor and cleanup changes bb9bbc2: fix local knowledge and startup stability 82c734e: Fix local knowledge retrieval and startup behavior 30749b8: Stabilize local knowledge and MCP flows 15c29ea: fix chat startup and stability regressions
Model hub / downloads | 3 | 180 | 63 | 9 | Cleaner Hugging Face URL handling, model routing, and MLX discoverability. | 9c2d47a: refactor(web-app): consolidate Hugging Face URL helpers de7fc77: refactor(server,huggingface): centralize URL cleanup and endpoint suffix stripping 5954ed8: refactor(server,tests): centralize upstream-header filtering and reuse hf URL helper in tests
Thread and conversation storage | 2 | 493 | 224 | 8 | More resilient message/thread persistence, including native fallback storage. | e26fba4: refactor: clean up thread storage handling and flag reads b507716: Add native storage fallback for conversations
Local model inference | 2 | 107 | 13 | 4 | Improved local model startup and streaming readiness paths. | 6888db8: Fix local MLX model discovery in Ax Studio e686922: Show MLX filter in model hub
Server / proxy hardening | 2 | 92 | 79 | 6 | Centralized CORS/header logic and hardened proxy/model route behavior. | bad4a8e: refactor(server): centralize CORS constants 0ba1f97: fix(server): correct CORS response header list length
General stability | 1 | 9 | 6 | 1 | Miscellaneous stability fixes and maintenance. | ba2e562: fix(core): align fallback events bridge typing

## Validation & Tests
Hash | Date | Commit Subject | Test Files Changed | Test Lines Added | Test Lines Deleted | Coverage Focus
c189427 | 2026-05-08 | chore: add local workspace files pending from sync | 2 | 76 | 0 | Startup / provider readiness
6888db8 | 2026-05-08 | Fix local MLX model discovery in Ax Studio | 1 | 58 | 0 | Local model inference
9c2d47a | 2026-05-08 | refactor(web-app): consolidate Hugging Face URL helpers | 1 | 32 | 1 | Model hub / downloads
de7fc77 | 2026-05-08 | refactor(server,huggingface): centralize URL cleanup and endpoint suffix stripping | 1 | 42 | 0 | Model hub / downloads
5954ed8 | 2026-05-08 | refactor(server,tests): centralize upstream-header filtering and reuse hf URL helper in tests | 1 | 10 | 9 | Model hub / downloads
a97c34b | 2026-05-08 | fix: address recent stability and model hub issues | 3 | 21 | 15 | Startup / provider readiness
82c734e | 2026-05-08 | Fix local knowledge retrieval and startup behavior | 3 | 9 | 95 | Local knowledge / MCP
30749b8 | 2026-05-08 | Stabilize local knowledge and MCP flows | 5 | 236 | 9 | Local knowledge / MCP
b507716 | 2026-05-08 | Add native storage fallback for conversations | 2 | 154 | 13 | Thread and conversation storage
15c29ea | 2026-05-08 | fix chat startup and stability regressions | 11 | 136 | 38 | Local knowledge / MCP
ae7097d | 2026-05-08 | chore: tighten stability cleanup coverage | 3 | 15 | 3 | Local knowledge / MCP
16ba001 | 2026-05-08 | Stabilize chat startup tools and quality coverage | 13 | 271 | 35 | Startup / provider readiness
c735ea6 | 2026-05-08 | Harden quality tests and update reports | 40 | 385 | 79 | Local knowledge / MCP
c321409 | 2026-05-09 | Improve local inference readiness and stability | 7 | 744 | 23 | Startup / provider readiness
f3cc955 | 2026-05-09 | Wait for local model startup before streaming | 1 | 59 | 0 | Startup / provider readiness
197abef | 2026-05-09 | Avoid local chat startup deadlock | 1 | 14 | 8 | Startup / provider readiness