## Summary & Recommendation
ax-intelligence = Superset engine + OUR UI (a revamp)
Prepared for Akira (CTO) • 2026-06-24 • Analysis only • CORRECTED: we REUSE Superset, not rebuild it
THE PLAN | ax-intelligence is a SEPARATE open-source product that USES Apache Superset as its base BI engine, with OUR OWN UI, branding and AI layer on top. A revamp / reskin — NOT a from-scratch rebuild.
What we REUSE | Superset's whole engine: charts/visualizations, SQL Lab, database connectors, dashboards, RLS, APIs. We do NOT rebuild these.
What is OURS (NEW) | The UI shell, navigation, branding/theme, and the AI layer (natural-language query, auto-insights). This is the differentiator.
Still a NO | Do NOT fork/merge Superset INTO ax-studio (the desktop app). Server-vs-desktop mismatch stands. ax-intelligence is its own product; ax-studio CONNECTS to it.
How much UI is ours | Use the 'custom shell + embed' level (Level 2): build our own app around Superset's embedded charts. Do NOT hard-fork Superset's frontend (maintenance trap).
Trade we accept | Superset as base = we keep its server stack (Python+Postgres+Redis+Celery). ax-intelligence is a hosted/Docker product, not local-first. In exchange we skip years of rebuilding BI.
Why this is good | Fast to a real product, mature BI for free, AI is our edge, we own the look & feel. This is exactly the Preset.io model (built by Superset's own creators).
The one rule | Stay close to upstream Superset. Reskin + wrap + add AI. The moment you heavily fork Superset's internals, maintenance cost explodes.

## Reuse vs Build New
What we REUSE from Superset vs What we BUILD ourselves
Correcting the earlier framing: most of it is REUSED. We build the shell + AI only.
Component | Source | Effort for us
Charts & visualizations (50+ types) | REUSE Superset | None — reused
SQL Lab / data exploration | REUSE Superset | None — reused
Database connectors (SQLAlchemy) | REUSE Superset | None — reused
Dashboard engine | REUSE Superset | None — reused
Row-level security / permissions | REUSE Superset | Config only
REST API / embedded SDK | REUSE Superset | Integrate only
Backend server (Flask/Postgres/Redis/Celery) | REUSE Superset | Run / host it
App UI shell & navigation | BUILD (ours) | Medium
Branding / theme | BUILD (ours) | Low–Medium
AI layer: natural-language query | BUILD (ours) | Medium–High — our edge
AI layer: auto-insights / reports | BUILD (ours) | Medium–High — our edge
ax-studio connector | BUILD (ours) | Low — like MCP/provider
BOTTOM LINE | ~70% reused from Superset, ~30% built by us (shell + AI). NOT a rebuild.

## UI Strategy (how ours)
How much of the UI is 'ours' — 4 levels
Recommended: Level 2 (custom shell + embed). Avoid Level 3 (hard fork).
Level | What we do | UI control | Maintenance cost | Verdict
1. Theme & brand | Use Superset's built-in theming: colors, logo, fonts | Low–Med | Low (upgrade-safe) | Easy but still looks like Superset
2. Custom shell + embed | Build OUR app UI/nav/branding/AI; embed Superset's charts via SDK | High outside / Med inside | Medium | RECOMMENDED — sweet spot
3. Fork the frontend | Fork superset-frontend and rewrite components | High | VERY HIGH forever | Avoid — merge-conflict trap
4. New UI on REST API | 100% new UI driving Superset via API | Total | High + blocked | Authoring API too immature

## Head-to-Head
Plain Superset (as-is) vs ax-intelligence (Superset-based revamp)
Both use Superset as engine. Difference = our UI + AI + separate product. Green = better.
Dimension | Plain Superset embedded | ax-intelligence (revamp on Superset) | Winner
Reuses Superset engine | Yes | Yes | Same
Look & feel is ours | No — Superset's UI | Yes — our shell & brand | ax-intelligence
AI-native features | No | Yes — our differentiator | ax-intelligence
Own product / roadmap | No | Yes | ax-intelligence
Time to first demo | Fastest | Fast (a bit more) | Plain Superset
Engineering effort | Lowest | Medium (shell+AI only) | Plain Superset
Mature BI reused (charts/SQL/connectors) | Yes | Yes | Same
Server stack required | Yes | Yes | Same
Local-first / no Docker | No | No | Same
Open-source product story | Weak (it's just Superset) | Strong (our OSS product) | ax-intelligence
Differentiation / market value | Low | High | ax-intelligence
Maintenance (if Level 2, no fork) | Low | Low–Medium | Plain Superset
Maintenance (if Level 3 fork) | n/a | Very high — AVOID | Plain Superset
Belongs inside ax-studio? | No | No — separate, connects in | Same
TALLY | Plain Superset better: 4 | ax-intelligence better: 5 | Same: 5

## Risks & Blockers
Risks & Blockers (Superset-based ax-intelligence)
Risk | Severity | Detail
Forking Superset frontend | High | Hard-forking superset-frontend = endless merge conflicts on every upstream release. Stay at Level 2 (embed), don't fork.
Server stack to run | Medium | Keeps Python+Postgres+Redis+Celery. Real DevOps; not local-first.
Docker / hosting needed | Medium | ax-intelligence must be hosted or run via Docker; not shippable as a pure desktop app.
Authoring API immaturity | Medium | Don't build chart-creation on the REST API; let Superset's own (themed) explore UI author, our UI consumes + AI.
Upstream divergence | Medium | Heavy customization drifts from upstream. Keep changes additive/wrapping, not invasive.
RLS pitfalls | Medium | RLS bypassed by SQL Lab, needs indexed columns, etc. Config carefully.
AI layer is the real new work | Medium | Most of OUR effort/value is the NL-query + insights layer — scope it well.
Putting it inside ax-studio | Blocker | Still wrong. ax-intelligence is a separate product ax-studio connects to.
License | Low | Apache-2.0 — free to reskin/build on; keep NOTICE/attribution.

## Recommended Plan
Recommended Plan — ax-intelligence on Superset
Reuse Superset, add our shell + AI, stay Level 2.
Phase | Goal | Activities | Output
Phase 0 — Decide | Direction set | This memo + Excel. ax-intelligence = Superset base + our UI. | DONE
Phase 1 — Stand up base | Run the engine | Superset via Docker; theme it (Level 1); enable embedding + API. | Themed Superset running
Phase 2 — Our shell | Make it ours | Build app shell, nav, branding; embed Superset charts/dashboards via SDK. | ax-intelligence UI v0
Phase 3 — AI layer | The differentiator | Natural-language query -> Superset; auto-insights; reports. This is our edge. | AI-native BI MVP
Phase 4 — Connect & harden | Ship | ax-studio connector; auth/RLS; perf; packaging; docs; OSS release. | ax-intelligence v1